# Updated A-Z Onboarding Document

# Updated A-Z Onboarding Document

This document outlines the complete, step-by-step client onboarding process, integrating the original A-Z technical setup with the newly structured dependency and communication framework.

# Core Principles

- Gated Workflow: Tasks only begin when their required input (milestone) is completed.

- Clear Communication: Client communication is tied to specific stage changes, not internal confusion.

- Systematic Readiness: Launch readiness is a calculated state based on QA and department completion.

# Phase 1: New Client Paid & Activation

This phase kicks off once a new client has formally agreed to the terms of service and completed the payment. It involves critical actions by the Closer and automated steps to initiate the onboarding journey.

## Actions & Dependencies

- Closer fills out the New Client Form (Business Name, Client Name, Email, Phone, Contract, Offer, etc.).

- Automation triggers: Slack notification to the team, GHL contact creation, Manager assignment, Slack channel creation (General & Scheduling), and ClickUp main onboarding task creation.

## Communication

- Internal: Slack notification alerts the team.

- Client-facing: No direct communication yet beyond the sales handoff.

# Phase 2: Welcome Email & CSM Outreach

This phase focuses on formally welcoming the client, providing essential resources, and scheduling the onboarding call.

## Actions & Dependencies

- Automation sends the Onboarding Welcome Email (includes Onboarding Form link, contract reminder, Slack/Skool sign-in).

- CSM is notified internally to prepare for engagement.

- CSM calls the client to welcome them, schedule the Onboarding Call, and remind them to complete the Onboarding Form.

## Communication

- Client-facing: Welcome email sent; CSM phone call.

# Phase 3: Onboarding Form Submitted

The client submits the detailed onboarding form, providing critical information for technical setup and A2P registration.

## Actions & Dependencies

- Blocked until: Client submits the Onboarding Form.

- Automation triggers: Slack notification, ClickUp task updated with onboarding info, Google Drive folder created, resource links added.

- Tech team begins A2P Verification process if EIN is provided.

## Communication

- Internal: Slack notification informs the team.

# Phase 4: Pre-Call Review & Onboarding Call

The CSM prepares for and conducts the onboarding call to align on strategy, expectations, and next steps.

## Actions & Dependencies

- CSM completes Pre-Call Checklist (reviews form, contract, sales notes).

- Onboarding Call takes place: Establish leadership, build implementation pathway, get FB/CRM access, get assets, set ROI projections, and book the Launch Call.

- CSM fills out the Kickoff Form to confirm all details.

## Communication

- Client-facing: Live Onboarding Call.

# Phase 5: Kickoff Completed & Implementation

With the strategy aligned and kickoff form submitted, the focus shifts to the technical and media setup.

## Actions & Dependencies

- Blocked until: Kickoff Form is submitted.

- Tech Team Tasks: Phone number setup, edit custom values, configure calendars, funnel design, AI Bot (Closebot) setup, call center setup.

- Media Buyer Tasks: Data & pixel configuration, Facebook Ads buildout, update fulfillment tracker.

## Communication

- Client-facing: Slack General channel for questions/issues; Slack Scheduling channel for appointments.

# Phase 6: Quality Assurance (QA)

Internal quality assurance checks on the technical and media setup before launch.

## Actions & Dependencies

- Blocked until: Department implementation tasks are completed.

- Tech QA: Check A2P, funnel (price, color, offer, mobile view), calendar integration, triggers.

- Media Buyer QA: Check campaign name, budget, page/ad account, offer details, landing page link, pixel.

- QA Form submission automatically updates the main ClickUp task.

## Communication

- Internal: QA confirmation and launch readiness signal.

# Phase 7: Launch Call & Go-Live

The final comprehensive walkthrough with the client and the official launch of their campaigns.

## Actions & Dependencies

- Blocked until: QA is fully completed and approved.

- CSM conducts Launch Call: Set expectations, show assets created, book 7-day check-in.

- Project Manager does final check-in (ads, funnels, payments).

- Fulfillment manager fills out Launch Form to notify team and client that ads are live.

## Communication

- Client-facing: Live Launch Call; Launch notification message.